Annex I

TENDER SPECIFICATIONS

Support to the coordination of European GNSS Simulation and Testing Infrastructure

Table of Contents

I.	SPECIFICATIONS	3

I.1.	Introduction	3

I.2.	Purpose of the Contract	4

I.3.	List of Acronyms	5

I.4.	Tasks	6

I.4.1.	TASK 1 – MANAGEMENT	6

I.4.2.	TASK 2 – Analysis of present and future user needs	7

I.4.3.	TASK 3 – Survey of European GNSS Simulation Tools, Laboratories and Testbeds	8

I.4.4.	TASK 4 – European GNSS Simulation and Testing Infrastructure Definition	9

I.4.5.	TASK 5 – Implementation Roadmap for the European GSTI	11

I.5.	Project milestones and meetings	12

I.6.	Project duration	12

I.7.	Deliverables	12

I.7.1.	Reports and documents to produce	12

I.7.2.	Report format and publication	12

I.8.	Place of Performance	13

I.9.	Contract Value	13

II.	Terms of contract	14

II.1.	Terms of payment	14

II.2.	Financial guarantees	14

II.3.	Subcontracting	14

II.4.	Legal form to be taken by the grouping of service providers to whom the contract is awarded	14

III.	FORM AND CONTENT OF THE TENDER	15

III.1.	General	15

III.2.	Structure of the tender	15

III.2.1.	Section One: administrative proposal	15

III.2.2.	Section Two: Technical proposal	16

III.2.3.	Section Three: Financial proposal	17

IV.	ASSESSMENT AND AWARD OF THE CONTRACT	18

IV.1.	Exclusion criteria (exclusion of tenderers)	18

IV.1.1.	Evidence to be provided by the tenderers	19

IV.1.2.	Other cases of exclusion	19

IV.1.3.	Declaration	19

IV.2.	Administrative and financial penalties	20

IV.3.	SELECTION CRITERIA (SELECTION OF TENDERERS)	21

IV.3.1.	Economic and financial capacity – References required	21

IV.3.2.	Technical and professional capacity – References required	21

IV.4.	EVALUATION OF TENDERS – AWARD CRITERIA	21

IV.5.	Information for tenderers	23

IV.6.	Annexes	23

# SPECIFICATIONS

## Introduction

In the recent years, the signals broadcast by the currently operational Global Navigation Satellite Systems (GNSS's) have become the basis for an emerging industry of innovative services and applications. So far, the developers of such technologies have relied upon the open signals transmitted by the present active systems, the American GPS and the Russian GLONASS. The perimeter of GNSS applications and services is about to evolve drastically in the forthcoming years driven by both, the advent of new systems such as the European Galileo and the Chinese COMPASS, and the modernisation and replenishment of the existing GNSS constellations. The public user community will benefit from an increased number of new navigation signals featuring superior tracking performance, available for positioning and timing. Moreover, new services such as Galileo SoL will be provided at global scale. This future multi GNSS panorama should prompt industry to improve their current GNSS based products and applications, and to devise and develop brand-new ones.

The envisaged benefits of the Galileo programme will be easier to accomplish if the mechanisms favouring its penetration in the global market are ready in due time. It is thus crucial that products capable of exploiting the benefits of the new signals and services are available by the time Galileo starts transmitting its first signals. If Europe intends to play a leading role in the future GNSS business, it is mandatory to start developing these new technologies as soon as possible. The main challenge for the private sector is the completion of these developments in due time prior to the transmission of the real Galileo signals from space.

The signals currently transmitted by the GIOVE-A satellite, the first prototype of a Galileo satellite, allow users to perform a certain level of equipment testing. Whilst GIOVE-A flies representative Galileo orbits and transmits Galileo like navigation signals, it is definitely not sufficient to support effectively the whole development and verification process for Galileo based user equipment and services. High fidelity simulation tools should be put in place in order to mitigate the current testing deficiencies and act as gap filler until the Galileo constellation reaches its operational state. The role of simulation for testing is nevertheless, not only limited to such early stages in the Galileo programme. Simulation tools will also be necessary in the long term for the qualification and certification of new GNSS equipment and applications.

The Public Sector already identified simulation as a crucial enabler for the European GNSS related industry and has promoted the development of these technologies through several initiatives at European, national and regional level. The Navigation Laboratory at ESA/ESTEC, Galileo Test and Development Environment (GATE) promoted by the German authorities, and its Italian counterpart, the Galileo Test Range (GTR) are just some examples There still exists a significant risk of not exploiting their full potential if critical aspects such as standardisation and running costs are overlooked. The lack of common standards might downplay the exploitation of synergies among the different tools whilst access to these facilities may be limited by economical arguments, in the sense that they will only attract those users who are able to afford the service fees.

In order to avoid the scenarios exposed above, to maximise the public benefit and to decrease the overall development cost, the Public Sector has to undertake the necessary actions to guarantee the coordination of the different stakeholders involved. The intent of this tender is to launch appropriate actions to establish an efficient and complete simulation and testing environment for supporting the development of the future European GNSS industry.

## Purpose of the Contract

This study aims to define the roadmap for the coordination and harmonisation of the European GNSS simulation and testing infrastructure. The envisaged key objectives of this coordination exercise are the following:

- Ensure interoperability of GNSS simulation and testbed tools and facilities

- Identify gaps in the services/functionalities which are currently provided to the users

- Make available the GNSS simulation and testing infrastructure to any user in the EU

- Improve user's confidence on the services provided by the GSTI

In particular, the present contract aims to investigate current and future user needs for the development and testing of GNSS related equipment, carry out an in-depth analysis of the current and projected simulation and testing capabilities being built in Europe and provide recommendations for the definition of an harmonised European GNSS Simulation and Testing Infrastructure (GSTI) which should exploit the potential synergies among the systems/tools surveyed. Finally, the outcomes of the aforementioned tasks shall support the establishment of a roadmap for the implementation of the envisaged European GSTI system.

This contract includes the execution of the following tasks:

Task 1: Management

Task 2: Analysis of present and future user needs

Task 3: Survey of European GNSS simulation tools, laboratories and testbeds

Task 4: European GNSS Simulation and Testing Infrastructure Definition

Task 5: Implementation roadmap for the European GSTI

The study logic for the performance of the different activities proposed in this SoW is shown in the following chart

Figure 1Study Logic

The activities associated with these tasks are described in detail in the following sections.

## List of Acronyms

| ARTUS | Advanced Receiver Terminal for User Services |
| --- | --- |
| COMPASS | Future Chinese GNSS |
| EGNOS | European Global Navigation Overlay System |
| ESA | European Space Agency |
| ESTEC | European Space Research and Technology Centre |
| EU | European Union |
| EUROCAE | European Organization for Civil Aviation Equipment |
| GAMMA | Assisted Galileo/GPS/EGNOS Mass Market receiver |
| GATE | Galileo Test and Development Environment |
| GBAS | Ground Based Augmentation Systems |
| GIOVE | Galileo In-Orbit Validation Element |
| GIRASOLE | Galileo Integrity Receiver for Advanced Safety Of Life Equipment |
| GLONASS | Global Orbiting Navigation Satellite System |
| GNSS | Global Navigation Satellite System |
| GPS | Global Positioning Service |
| GREAT | Galileo REceiver for the mAss markeT |
| GR-POSTER | Galileo-Ready POSitioning TERminal |
| GSA | European GNSS Supervisory Authority |
| GSM | Global System for Mobile communications |
| GSTI | GNSS Simulation and Testing Infrastructure |
| GTR | Galileo Test Range |
| ICD | Interface Control Document |
| IEC | International Electrotechnical Commission |
| I/F | Interface |
| IPR | Intellectual Property Rights |
| MAGIC | MAnagement of Galileo Interferences and Counter measures |
| MEMS | Micro-Electro-Mechanical Systems |
| MOPS | Minimum Operational Performance Standard |
| OS | Open Service |
| RFP6 | 6th Research Framework Programme |
| RTCA | Radio Technical Commission for Aeronautics |
| SAR | Search And Rescue |
| SARPs | Standards and Recommended Practices |
| SBAS | Satellite Based Augmentation System |
| SIS | Signal In Space |
| SoL | Safety of Life |
| SoW | Statement of Work |
| UMTS | Universal Mobile Telecommunications System |
| UWB | Ultra WideBand |
| WIFI | Wireless Fidelity |
| 3GPP | Third Generation Partnership Project |

## Tasks

### TASK 1 – MANAGEMENT

#### Description

The task consists in providing the overall management for the contract. The main activities to be performed are:

- Contractual management

- Organization and coordination of project internal activities including internal communication flow

- Management of documents

- Tracking of project status

- Establish and maintain travel plan

- Review and verification of deliverables

- Organization of progress meetings (calling notice, agenda, chairing and reporting)

- Identify needs for interfaces with external entities

- Ensure coordination between the different activities as necessary

#### Deliverables

In addition to the deliverables identified below, the contractor shall also provide input to GSA's GNSS Knowledge Management Facility (GKMF) on request.

| Ref | Title | Delivery | Comments |
| --- | --- | --- | --- |
| D1.1 | Travel Plan | To+1 months |  |
| D1.2.x | Status Report | Every 3 months | Includes both technical and administrative status |
| D1.3 | Final Report | To+12 months |  |

#### Milestones

Progress meetings will be organised on a 3-monthly basis to present the status of the work and steer the next period. Depending on the development of the work, an ad-hoc technical coordination meeting further to those planned might be arranged by the customer if required. Additional technical coordination will be done through teleconference.

### TASK 2 – Analysis of present and future user needs

#### Description

The activities to be performed shall focus on the identification of functionalities required by the GNSS industry and research institutions to support the development of new user technologies based on the next GNSS generation and other emerging technologies. Those new technologies encompass both, new products or equipment and applications. The functionalities addressed in this task should cover a wide range of user needs, which are driven by the growing diversity of GNSS based equipment and services to be developed in a near future.

The contractor shall propose an appropriate methodology based on its own initial analysis. This analysis should cover all relevant aspects, at least the following (no exhaustive) list of items:

- Consult relevant user communities involved in the development of GNSS based technology and applications such as SME's, research institutions, universities, etc. This consultation process might be carried out through dedicated questionnaires, workshops or other valid means

- Identify common practises, tools and facilities used by industry to support the design, development, verification and qualification of standalone Mass Market (low-end) GNSS related equipment such as antennae, receivers, interferences, etc

- Analyse verification procedures and interface requirements for current hybrid devices which integrate additional technologies other than GNSS. Some of these hybrid products which combine GNSS with other technologies like pseudolites, GSM, UMTS, UWB, WIFI, MEMS, etc are already available on the market.

- Review available application and specific receiver standards (e.g. EUROCAE MOPS, IEC standard) and identify test procedures and tools required to support the certification of high-end GNSS equipment

- Assess the potential impacts in the identified testing and verification methodologies arising from the upcoming multi GNSS scenario

- Examine applicable standards and verification procedures for SAR equipment

- The experience accumulated during the past EU research initiatives should be capitalised to the maximum extent. During the execution of the tasks, the contractor will have the possibility to request results from specific FP6 projects dealing with user technologies (GREAT, GR-POSTER, ARTUS, SWIRLS, GIRASOLE and MAGIC). Nevertheless, the tenderers shall note that the access to FP6 outputs will be subject to the applicable IPRs and license agreements with third parties. If feasible, the following information should be analysed:

  - Verification and testing activities

  - Constraints on procedures and testing equipment and actions put in place to mitigate those limitations

  - Tools and simulators used/updated/developed to support and verification activities within the frame of a project.

- The derivation of user requirements for conducting large scale demos or tests. Some of the current testbeds offer wide outdoors testing areas which enable users to test their applications/equipment utilising both real navigation signals and additional simulated inputs

- Address specific requirements for specific services and applications (e.g. timing, indoor navigation, etc)

- Track latest GNSS based applications developed by industry and research institutions and devise additional testing and verification needs tailored to each case. In particular, the current ESA activities and demos on innovative GNSS based application will be analysed

The outcomes of the task listed above will be compiled in a deliverable document. The specific contents of this file will include:

- The complete set of functionalities to be provided by the harmonised GNSS Simulation and Testing infrastructure

- The whole range of test/use cases to be supported

#### Deliverables

In addition to the deliverables identified below, the contractor shall also provide input to GSA's GNSS Knowledge Management Facility (GKMF) on request.

| Ref | Title | Delivery | Comments |
| --- | --- | --- | --- |
| D2.1 | Report on industry standard procedures for testing and verification of GNSS and SAR related equipment and applications | To+3 months |  |
| D2.2 | Lessons learnt from RFP6 activities on testing and simulation needs | To+3 months |  |
| D2.3 | Report on required functionalities and use cases for the harmonised GNSS Simulation and Testing Infrastructure | To+5 months |  |

### TASK 3 – Survey of European GNSS Simulation Tools, Laboratories and Testbeds

#### Description

In the recent years the Public Sector, at European, national and regional levels, has promoted the development of specific tools such as simulators, navigation laboratories and testing environments with the purpose of boosting the growth of the European GNSS downstream industry.

These tools are intended to provide developers with appropriate means so that the new possibilities offered by the future satellite navigation systems, in particular Galileo, can be already tested and exploited. The objective of this work is to complete a thorough survey covering the most relevant tools and facilities in Europe, either existing or projected. The tools covered should include the most significant ESA developments and facilities on GNSS simulation.

The findings arising from the survey should provide a better understanding of the present installed capabilities across Europe. The outcome of this activity should provide at least detailed information on the following topics:

- General information on stakeholders and logistic such as ownership, builders, operator(s), (planned) date of entry into service, contact details, location, etc of the testing facility

- Scope and type of the tools/facilities surveyed. Since the requirements to be covered are rather heterogeneous, the tools to be analysed are expected to be very diverse. The scale of the equipment may vary as well from for instance a compact signal generator up to an open test range for demonstration of applications based on new navigation signals. Where applicable, a comprehensive analysis of the means used to integrate simulated and real inputs at user level shall be carried out

- Thorough analysis of the use cases for each tool/testbed, including a description of the functions and operational principles.

- Analysis of the user interfaces with the testing equipment. Where possible, provide this information based on the tool/facility ICD. Identify tool's services and functionalities which can be provided remotely to the users (e.g. via Internet)

- High level architectural description of the facility, where applicable, associating each of the components to the provided functionalities and use cases

- For each tool, address the following items:

  - Analyse the use of common standards at interface level

  - Tool's verification and qualification record. Level of maturity achieved by the tool

  - In the case of simulators, list and description of physical models embedded in the tool

  - Projected tool lifecycle, including planned evolutions and tool maintenance policy

  - Tool's associated IPRs

  - Ownership, commercial availability, price and license policy

  - Support to potential users offered by the operator of the facility (e.g. schedule, costs)

- Commercial policy for the tools/testing facilities, prices, rates, user fees, business calendar and business hours

#### Deliverables

In addition to the deliverables identified below, the contractor shall also provide input to GSA's GNSS Knowledge Management Facility (GKMF) on request.

| Ref | Title | Delivery | Comments |
| --- | --- | --- | --- |
| D3.1 | Survey report on European GNSS simulation and testing tools and facilities - Draft | To+4 months |  |
| D3.2 | Survey report on European GNSS simulation and testing tools and facilities - Final | To+6 months |  |

### TASK 4 – European GNSS Simulation and Testing Infrastructure Definition

#### Description

The objective of this work is to provide recommendations for the development of a reference GNSS simulation and testing environment in Europe for development of user segment equipment and applications. The potential users of this system are thus GNSS equipment manufacturers and application developers.

The European GNSS Simulation and Testing Infrastructures is intended to take advantage from accumulated know-how from similar national initiatives, and provide additional added value by

- Coordinating activities among several European projects at national/regional level, always depending on stakeholder's interests and willingness to participate

- Harmonising and standardising services, products, interfaces, etc

- Providing missing functionalities

- Assessing the level of qualification/certification required for the GSTI system components, based on the type of services to be provided by the GSTI system (e.g. support to the certification of SoL receivers)

- Improving user's confidence and reliability of test outcomes

- Providing commercial services and products openly to any interested user in the European Union

The following design solutions for the GSTI should by analysed taking into account the overall boundary conditions

- distributed architecture with geographical dispersion

- centralised architecture

Whilst the GSTI system should ideally provide all the functionalities identified in the course of Task 2 covering the complete set of user's needs, the intended solution for the testing infrastructure should seek, when appropriate, the maximum reuse of the tools and platforms surveyed. Therefore the outcomes expected from this task shall mainly rely on the careful assessment and exploitation of the outputs produced in the previous Task 3. The following activities (the list is not exhaustive) are expected to be performed:

- Link functionalities and user requirements specified in Task 2 to the tools surveyed in Task 3, identifying explicitly those functionalities not covered. The contractor should explore different options for adding functionalities not provided by the existing tools

- Assess potential synergies, both functional and operational, among the examined tools. Limitations for exploiting these synergies such as incompatibilities at interface level shall be analysed in detail, providing also feasible solution to overcome the encountered problems

- Provide recommendations on output products and external user interfaces for the GSTI system, considering recognised standards if possible. The access to the GSTI will be facilitated if all user I/F are properly identified and documented

- Propose standards applicable to the GSTI system according to those already used by the surveyed systems, with the objective of minimising the efforts required to upgrade the existing tools to the new standards

- Recommend a qualification strategy for the GSTI system components which have not reached the required maturity. Such qualification strategy might be supported by the cross-validation of the results produced by tools providing common functionalities. It is recalled that the intended system is expected to become a reference for any facility of this type in Europe. Therefore it is of utmost importance that only duly qualified components will be considered for integration in the final design

- Develop a preliminary operational concept for the devised system. The optimisation of the overall operational costs shall be an additional design driver. Savings in the operating costs can be achieved with a system design aiming to reduce the complexity of operations and favour the automation of tasks.

#### Deliverables

In addition to the deliverables identified below, the contractor shall also provide input to GSA's GNSS Knowledge Management Facility (GKMF) on request.

| Ref | Title | Delivery | Comments |
| --- | --- | --- | --- |
| D4.1 | Mapping matrix relating Tools and Functionalities | To+6 months |  |
| D4.2 | Concept for the European GSTI system | To+7 months |  |
| D4.3 | GSTI concept Justification File | To+8 months |  |
| D4.4 | Report on new components to be procured and required upgrades for the existing tools | To+8 months |  |
| D4.5 | GSTI specification | To+8 months |  |
| D4.6 | Preliminary GSTI USER ICD | To+9 months |  |
| D4.7 | Note on qualification strategies for equipment and tools | To+9 months |  |
| D4.8 | Preliminary operation concept for the European GSTI | To+10 months |  |

### TASK 5 – Implementation Roadmap for the European GSTI

#### Description

Further to the definition of the conceptual design for the European GSTI, the objective of this task is the completion of detailed implementation roadmap for the planned system, taking into account its qualification. The outcome document is expected to provide the guidelines for the successive activities aimed to the realisation of the GSTI system. It should also cover additional aspects such as coordination with the relevant stakeholders, like research institutes and European and national entities. The work to be performed shall include the following tasks:

- Identification of specific tasks to be performed during the implementation and qualification phases. Qualification shall be envisaged at component level and system level

- Establishment of an implementation logic including the identification of interfaces among the specific tasks and their arrangement in chronological order. The ordering of the specific activities shall be driven by the optimisation of the implementation costs, the level of priority of each task with respect to the needs identified in the GSTI specification, and the exploitation of synergies among the tasks.

- Estimation of efforts required to accomplish each of the tasks. The procedure put in place to produce these effort estimates must be documented and duly justified

- Risk assessment. The contractor shall identify problematic areas which might impact the performance of the activities

#### Deliverables

In addition to the deliverables identified below, the contractor shall also provide input to GSA's GNSS Knowledge Management Facility (GKMF) on request.

| Ref | Title | Delivery | Comments |
| --- | --- | --- | --- |
| D5.1 | Note on approach to estimation of efforts | To+10 months |  |
| D5.2 | Implementation roadmap for the European GSTI | To+12 months |  |

## Project milestones and meetings

The following meetings will be held between the Contractor and the GSA.

| Project Milestone | Review | Venue | Objective | Schedule |
| --- | --- | --- | --- | --- |
| Kick-Off Meeting | KOM | GSA | Authorization of the start of project activities by GSA. Clarify and settle open points and details of the project. | T0 |
| Progress Meeting | PM1 | GSA | Approve deliverables. Provide guidance and steer the activities for the next period | T0 + 3 months |
| Intermediate Review | IR | GSA | Approve deliverables. Provide guidance and steer the activities for the next period | T0 + 6 months |
| Progress Meeting | PM2 | GSA | Approve deliverables. Provide guidance and steer the activities for the next period | T0 + 9 months |
| Final Acceptance Review | FAR | GSA | Draw conclusions on the project outcome. Collect recommendations for future work. Approve final deliverables. | T0 + 12 months |
| Technical Coordination Meeting (Optional) | TCM | GSA | Progress on specific topics. Steer project activities in case major deviation from original planning are identified | N.A. |

## Project duration

The project activities shall start at T0 and will end after an estimated period of 12 months (after successful completion of the FAR).

## Deliverables

### Reports and documents to produce

The precise nature of the deliverables and reports required is specified under each individual task

description in sections I.2. and I.4. above. The GSA shall have 30 days from receipt to approve or reject the reports and documents. Within 15 days of receiving the GSA's comments or request for clarification, the contractor will submit additional information or another report.

### Report format and publication

3 copies of the reports shall be supplied in paper form and one copy in electronic form, either

in MS Word or in HTML format.

## Place of Performance

The task will be performed at the Contractor's premises.

Meetings between the Contractor and the GSA shall be held at GSA's premises in Brussels (unless stated otherwise). All cost foreseen in the performance of the project, including travel costs shall be borne by the Contractor.

## Contract Value

The maximum allocated budget for the contract is 500.000 Eur (VAT excluded).

# Terms of contract

In drawing up his offer, the tenderer should bear in mind the provisions of the draft Contract attached to this invitation to tender. Any limitation, amendment or denial of the terms of contract will lead to automatic exclusion from the procurement procedure.

GSA may, before the contract is signed, either abandon the procurement procedure or cancel the award procedure without the tenderers being entitled to claim any compensation.

## Terms of payment

Payments shall be made in accordance with the provisions specified in the service Contract.

## Financial guarantees

Guarantee on pre-financing

For any pre-financing higher than 100,000 EUR, a financial guarantee equivalent to the amount of the pre-financing will be requested.

Depending on the financial situation of the tenderer, GSA may ask for the financial guarantee for amounts lower than 100,000 EUR.

## Subcontracting

If the tenderer intends to subcontract part of the service, he shall indicate in his offer which part will be subcontracted and to what extend (% of the total contract value).

Tenderers must inform the subcontractor(s) that Article II.17 of the Contract will be applied to them. Once the Contract has been signed, Article II.13 of the above-mentioned contract shall govern the subcontracting.

## Legal form to be taken by the grouping of service providers to whom the contract is awarded

Groupings, irrespective of their legal form, may submit bids. Tenderers may, after forming a grouping, submit a joint bid on condition that it complies with the rules of competition. Such groupings (or consortium) must specify the company or person heading the project and must also submit a copy of the document authorising this company or person to submit a bid. If awarded, the contract will be signed by the company of the person heading the project, who will be, vis à vis GSA, the only contracting party responsible for the performance of this contract. Tenders from a consortium of firms or groups of service providers, contractors or suppliers must specify the role, qualifications and experience of each member of the consortium or group. Each member must provide all the necessary documents for assessing the bid as a whole with regard to the exclusion criteria, selection criteria (all of them) and award criteria.

# FORM AND CONTENT OF THE TENDER

## General

Tenders must be written in one of the official languages of the European Union. However, and due to the technical nature of the project, tenders are invited to submit their bids (or at least the technical part thereof) preferably in English.

Tenders must be clear and concise, with continuous page numbering, and assembled in a coherent fashion (e.g. bound or stapled, etc…). Since tenderers will be judged on the content of their submitted bids, they must make it clear that they are able to meet the requirements of the specifications.

## Structure of the tender

All tenders must include three sections i.e. an administrative, a technical and a financial proposal.

### Section One: administrative proposal

This section must provide the following information, set out in the standard identification forms attached to these tender specifications (Annexes 1, 2 and 3):

- Tenderers’ identification (Annex 1)

- All tenderers must provide proof of registration, as prescribed in their country of establishment, on one of the professional or trade registers or provide a declaration or certificate.

- If the tenderer is a natural person, he/she must provide a copy of the identity card/passport or driving licence and proof that he/she is covered by a social security scheme as a self-employed person.

Each service provider (including subcontractor(s) or any member of a consortium or grouping) must complete and sign the identification forms in Annex 1 and also provide above-mentioned documents. However, the subcontractor(s) shall not be required to fill in or provide those documents when the services represent less than 10% of the contract.

- Financial identification (Annex 2)

The bank identification form must be completed and signed by an authorised representative of the tenderer.  In the case of a grouping, this form must only be provided by the person heading the project.

- Legal entities (Annex 3)

The legal entity form in Annex 3 must be completed in and should be accompanied by requested supporting documents. In the case of a grouping, this form must only be provided by the person heading the project.

GSA reserves the right, however, to request additional evidence in relation to the bid submitted for evaluation or verification purposes within a time-limit stipulated in its request.

### Section Two: Technical proposal

This section is of great importance in the assessment of the bids, the award of the contract and the future execution of any resulting contract.

Some guidelines are given below, but attention is also drawn to the award criteria, which define those parts of the technical proposal to which the tenderers should pay particular attention. The technical proposal should address all matters laid down in the specifications. The level of detail of the tender will be extremely important for the evaluation of the tender.

The technical proposal shall include a preliminary list of tools, testbeds and facilities which the tenderer intends to survey in the frame of Task 3. Tenderers are asked to keep the scope of this task within reasonable limits so as not to compromise the efforts required for the remaining tasks.

Tenderers must present in their bids a proposal on the methodology and the organisation of the work to carry out in the framework of the study. In particular, the technical proposal shall include a set of detailed work-package descriptions that identify the contractual and non-contractual outputs (if any) to be produced in the frame of the contract and will detail the interfaces to be established with external entities to perform the work required. The technical proposal shall include a detailed schedule. The technical proposal shall include a detailed allocation of task per partner. A detailed description of the deliverables shall also be presented.

The technical proposal shall include a detailed travel plan that covers both internal coordination meetings and attendance to external standardisation fora. This travel plan shall include a list of meetings, expected location, planned duration, planned attendance from the consortium, objective for attendance and estimated cost.

Tenderers shall describe as part of their technical proposal all prior experience relevant to perform the work requested.

The technical proposal shall include, for each task, a list of expected input material to be provided by GSA. This list of input material shall be limited to documents strictly required to perform the work and shall be duly justified.

Tenderers shall submit, as part of the technical proposal, CVs for key personnel involved in the different tasks.

Tenderers shall provide a detailed proposal of how each task would be carried out, and by whom, including the division of work among the different categories of staff on a man/days basis.

The technical proposal must provide all the information needed for the purpose of awarding the contract.

### Section Three: Financial proposal

All tenders must contain a financial proposal. The tenderer's attention is drawn to the following points:

- Prices must be quoted in euros, including the countries which are not in the euro-area. As far as the tenderers of those countries are concerned, they cannot change the amount of the bid because of the evolution of the exchange rate. The tenderers choose the exchange rate and assume all risks or opportunities relating to the rate fluctuation.

- Prices must be fixed amounts and include all expenses, such as travel expenses and daily allowances.

- Prices should be quoted free of all duties, taxes and other charges, i.e. also free of VAT, as the Communities are exempt from such charges in the EU under Articles 3 and 4 of the Protocol on the Privileges and Immunities of the European Communities of 8 April 1965 (OJ L 152 of 13 July 1967). Exemption is granted to GSA by the governments of the Member States, either through refunds upon presentation of documentary evidence or by direct exemption. For those countries where national legislation provides an exemption by means of a reimbursement, the amount of VAT is to be shown separately. In case of doubt about the applicable VAT system, it is the tenderer's responsibility to contact his or her national authorities to clarify the way in which the European Community is exempt from VAT;

- Prices shall be fixed and not subject to revision during the performance of the contract.

- For each category of staff involved in the project, the tenderer must specify:

- the total labour costs;

- the daily rates

- the number of actual man-days needed to carry out the work, split up per staff member involved

- other categories of costs, indicating the nature of the cost, the total amount, the unit price and the quantity.

Bids involving more than one service provider (consortium) must specify the amounts indicated above for each provider.

# ASSESSMENT AND AWARD OF THE CONTRACT

The assessment will be based on each tenderer's bid.

All the information will be assessed in the light of the criteria set out in these specifications. The procedure for the award of the contract, which will concern only admissible bids, will be carried out in three successive stages.

The aim of each of these stages is:

1)	to check on the basis of the exclusion criteria, whether tenderers can take part in the tendering procedure;

2)	to check on the basis of the selection criteria, the technical and professional capacity and economic and financial capacity of each tenderer;

3)	to assess on the basis of the award criteria each bid which has passed the exclusion and selection stages.

The contract will be concluded with the tenderer ranked best when the bids are evaluated.

## Exclusion criteria (exclusion of tenderers)

To be eligible for participating in this contract award procedure, tenderers must not be in any of the following exclusion grounds:

(a)	they are bankrupt or being wound up, are having their affairs administered by the courts, have entered into an arrangement with creditors, have suspended business activities, are the subject of proceedings concerning those matters, or are in any analogous situation arising from a similar procedure provided for in national legislation or regulations;

(b)	they have been convicted of an offence concerning their professional conduct by a judgement which has the force of res judicata;

(c)	they have been guilty of grave professional misconduct proven by any means which the contracting authority can justify;

(d)	they have not fulfilled obligations relating to the payment of social security contributions or the payment of taxes in accordance with the legal provisions of the country in which they are established or with those of the country of the contracting authority or those of the country where the contract is to be performed;

(e)	they have been the subject of a judgement which has the force of res judicata for fraud, corruption, involvement in a criminal organisation or any other illegal activity detrimental to the Communities' financial interests;

(f)	following another procurement procedure or grant award procedure financed by the Community budget, they have been declared to be in serious breach of contract for failure to comply with their contractual obligations;

### Evidence to be provided by the tenderers

1.	GSA shall accept, as satisfactory evidence that the tenderer is not in one of the situations described in point (a), (b) or (e) above, the production of a recent extract from the judicial record or, failing that, a recent equivalent document issued by a judicial or administrative authority in the country of origin or provenance showing that those requirements are satisfied.

2.	GSA accepts, as satisfactory evidence that the tenderer is not in the situation described in point (d) above, a recent certificate issued by the competent authority of the State concerned.

Where no such certificate is issued in the country concerned, it may be replaced by a sworn or, failing that, a solemn statement made by the interested party before a judicial or administrative authority, a notary or a qualified professional body in his country of origin or provenance.

The documents referred to in paragraph 1 and 2 shall relate to legal and/or natural persons including, if applicable with regard to points b) and e), company directors or any person with powers of representation, decision-making or control in relation to the tenderer.

### Other cases of exclusion

Contracts will not be awarded to tenderers who, during the procurement procedure:

a)	are subject to a conflict of interest;

Tenderers must declare:

  - that they do not have any conflict of interest in connection with the contract; a conflict of interest could arise in particular as a result of economic interests, political or national affinities, family or emotional ties, or any other relevant connection or shared interest;

  - that they will inform the contracting authority, without delay, of any situation constituting a conflict of interest or which could give rise to a conflict of interest;

  - that they have not made and will not make any offer of any type whatsoever from which an advantage can be derived under the contract;

  - that they have not granted and will not grant, have not sought and will not seek, have not attempted and will not attempt to obtain, and have not accepted and will not accept, any advantage, financial or in kind, to or from any party whatsoever, constituting an illegal practice or involving corruption, either directly or indirectly, as an incentive or reward relating to the award of the contract.

GSA reserves the right to check the above information.

b)	are guilty of misrepresentation in supplying the information required by the contracting authority as a condition of participation in the contract procedure or fail to supply this information.

### Declaration

Tenderers must fill in and sign the forms attached to the specifications (Annex 4).

Where the bid involves more than one service provider (consortium or grouping), each provider must fill in and return the form, as well as the evidence specified in pt IV.1.1.

Subcontractors (when the subcontracted part exceeds 20% of the contract) must only provide the form in Annex 4.

Bids submitted by subcontractors which have not provided the abovementioned documents may not be taken into consideration.

GSA reserves the right, however, to request any other document relating to the proposed tender for evaluation and verification purpose, within a delay fixed in its request.

## Administrative and financial penalties

1.	Without prejudice to the application of penalties laid down in the contract, candidates or tenderers and contractors who have been guilty of making false declarations or have been found to have seriously failed to meet their contractual obligations in an earlier procedure will be excluded from all contracts and grants financed by the Community budget for a maximum of two years from the time when the infringement is established, as confirmed after an adversarial procedure with the contractor.

That period may be extended to three years in the event of a repeat offence within five years of the first infringement.

Tenderers or candidates who have been guilty of making false declarations will also incur financial penalties representing 2% to 10% of the total value of the grant being awarded.

Contractors who have been found to have seriously failed to meet their contractual obligations will incur financial penalties representing 2% to 10% of the value of the grant in question.

This rate may be increased to 4% to 20% in the event of a repeat offence within five years of the first infringement.

2. 	In the cases referred to in points IV.1, a), c), d), the candidates or tenderers will be excluded from all contracts and grants for a maximum of two years from the time when the infringement is established, as confirmed after an adversarial procedure with the contractor.

In the cases referred to in points IV.1, b) and e), the candidates or tenderers will be excluded from all contracts and grants for a minimum of one year and a maximum of four years from the date of notification of the judgment. Those periods may be extended to five years in the event of a repeat offence within five years of the first infringement or the first judgment.

3. 	The cases referred to in point IV.1, e) cover:

a) cases of fraud as referred to in Article 1 of the Convention on the protection of the European Communities' financial interests established by the Council Act of 26 July 1995 (OJ/C 316 of 27.11.1995, p. 48);

b) cases of corruption as referred to in Article 3 of the Convention on the fight against corruption involving officials of the European Communities or officials of Member States of the European Union, established by the Council Act of 26 May 1997 (OJ/C 195 of 25.6.1997, p. 1);

c) cases of participation in a criminal organisation, as defined in Article 2(1) of Joint Action 98/733/JHA of the Council (OJ/L 315 of 29.12.1998, p. 1);

d) cases of money laundering as defined in Article 1 of Council Directive 91/308/EEC (OJ/L 166 of 28.6.1991, p.77).

## SELECTION CRITERIA (SELECTION OF TENDERERS)

To be eligible, the tenderers must have the economic and financial capacity as well as the technical and professional capacity to perform the tasks required in this call for tender.

### Economic and financial capacity – References required

Tenderers must provide proof of their financial and economic capacity by means of the following documents: the balance sheets or extracts from balance sheets for the last three financial years, and a statement of overall turnover and turnover relating to the relevant services for the last three financial years.

This rule applies to all service providers, regardless of the percentage of tasks they intend to execute, once they have chosen to submit a tender. However, if the tender includes subcontractors whose tasks represent less than 20% of the contract, those subcontractors are not obliged to provide evidence of their economic and financial capacity.

### Technical and professional capacity – References required

Tenderers must provide evidence of their technical and professional competence on the following points:

- Thorough understanding of global satellite navigation systems and augmentation technologies

- Good knowledge of standards applicable to the manufacturing of GNSS terminals

- Familiarity with GNSS signal simulator technologies

- Familiarity with GNSS user receiver technologies and integration of GNSS with additional sensors

- Good knowledge of the present GNSS application portfolio in several user domains

- Demonstrated experience on any of these fields:

  - verification and qualification of GNSS technologies

  - GNSS performance simulation

If several service providers/subcontractors are involved in the bid, each of them must have and show that they have the professional and technical capacity to perform the specific tasks assigned to them.

Tenderers should provide with their bid detailed curriculum vitae of each staff member responsible for carrying out the work, including his or her educational background, degrees and diplomas, professional experience, research work, publications and linguistic skills.

The CV's shall be presented, preferably, in accordance to GSA Recommendation on a common European format for curricula vitae, published in OJ L79 of 22 March 2002, p. 66.

## EVALUATION OF TENDERS – AWARD CRITERIA

The contract will be awarded according to the criteria given below, on the basis of the economically most advantageous tender.

Only bids that have reached a total score of a minimum of 70% and a minimum score of 60 % for each technical criterion will be taken into consideration for awarding the contract.

a) Technical evaluation criteria as weighted

| N° | Award Criteria | Weighting |
| --- | --- | --- |
| 1 | Understanding of the requirements and objectives and discussion of problem areas - Quality of content of the technical proposal .Bidder analysis of the requirements .Understanding of the environment under which the study is conducted .Understanding of the GSA's needs and preliminary analysis of solutions .Critical review of the requirements .Analysis of interface requirements between the different tasks - Compliance to Statement of Work - Completeness - Relevance of proposed options | 30 |
| 2 | Quality and suitability of proposed work programme and adequacy of approach - Quality of the Work Package Descriptions - Adequacy of the allocation of the tasks per partner - Adequacy of the effort related to each activity - Confidence that the work programme is appropriate to meet the requirements | 40 |
| 3 | Adequacy of management and planning for the execution of the work - Adequacy of reporting scheme - Adequacy of management level of effort - Quality of proposed planning - Heritage and experience of the proposed team | 30 |
| Total number of points | 100 |

b) Total price

Total number of points for price: X (Where X is the highest score for technical evaluation reached by an eligible offer).

Score for price for offer (a) will be then be computed as follows: X * lowest price among eligible offers / price of offer (a)

The contract will be awarded to the tenderer that offers the best quality price score as measured by the following formula:

70% * (Total number of points for technical evaluation) + 30% * (Total number of points for price)

## Information for tenderers

GSA will inform tenderers of decisions reached concerning the award of the contract, including the grounds for any decision not to award a contract or to recommence the procedure.

If a written request is received, GSA will inform all rejected tenderers of the reasons for their rejection and all tenderers submitting an admissible tender of the characteristics and relative advantages of the selected tender and the name of the successful tenderer.

However, certain information may be withheld where its release would impede law enforcement or otherwise be contrary to the public interest, or would prejudice the legitimate commercial interests of economic operators, public or private, or might prejudice fair competition between them.

## Annexes

- Identification of the Tenderer

- Financial Identification

- Legal Entity Form

- Declaration by the Tenderer (relating to the exclusion criteria)

- Draft Contract

ANNEX 1

IDENTIFICATION OF THE TENDERER

(Each service provider, including subcontractor(s) or any member of a consortium or grouping, must complete and sign this identification form)

Call for tender GSA/OP/08/07

| Identity |
| --- |
| Name of the tenderer |  |
| Legal status of the tenderer |  |
| Date of registration |  |
| Country of registration |  |
| Registration number |  |
| VAT number |  |
| Description of statutory social security cover (at the level of the Member State of origin) and non-statutory cover (supplementary professional indemnity insurance) |  |
| Address |
| Address of registered office of tenderer |  |
| Where appropriate, administrative address of tenderer for the purposes of this invitation to tender |  |
| Contact Person |
| Surname: First name: Title (e.g. Dr, Mr, Ms) : Position (e.g. manager): Telephone number: Fax number: E-mail address: |  |
| Legal Representatives |
| Names and function of legal representatives and of other representatives of the tenderer who are authorised to sign contracts with third parties |  |
| Declaration by an authorised representative of the organisation I, the undersigned, certify that the information given in this tender is correct and that the tender is valid. |
| Surname: First name: | Signature: |

ANNEX 2 - Financial Form

(to be completed by the tenderer)

The tenderer's attention is drawn to the fact that this document is a model and that a specific Financial Form for each Member State is available at the following Internet address: http://gsa.europa.eu/, under the "Call for tender" section

ANNEX 3 - Legal Entity Form

(to be completed by the tenderer)

The tenderer's attention is drawn to the fact that this document is a model and that a specific Legal Entity Form for each Member State is available at the following Internet address: http://gsa.europa.eu/, under the "Call for tender" section

Please note that we can only accept either original documents or certified copies, which must be less than 6 months old.

In the case of a grouping, this form must only be provided by the person heading the

project.

ANNEX 4

DECLARATION BY THE TENDERER

Each service provider, including subcontractor(s) or any member of a consortium or grouping, must sign this identification form

1.	In accordance with Article 93 of the Financial Regulation of the European Communities (Council Regulation 1605/2002 of 25.6.2002) published in Official Journal L 248 of 16 September 2002, I declare on my honour that I am not in any of the following situations which would exclude me from participating in this procurement procedure:

a)	I am not bankrupt, being wound up or having my affairs administered by the courts, I have not entered into an arrangement with creditors, I have not suspended business activities, I am not the subject of proceedings concerning any such matters, and I am not in any similar situation arising from a similar procedure provided for in legislation or regulations;

b)	I have not been convicted of an offence concerning my professional judgement by a judgment which has the force of res judicata;

c)	I have not been found guilty of grave professional misconduct proven by any means which the contracting authority can justify;

d)	I have not failed to fulfil obligations relating to the payment of social security contributions or the payment of taxes in accordance with the legal provisions of the country in which I am established or with those of the country or the contracting authority or those of the country where the contract is to be performed;

e)	I have not been the subject of a judgment which has the force of res judicata for fraud, corruption, involvement in a criminal organisation or any other illegal activity detrimental to the Communities' financial interests;

f)	as a consequence of another procurement or grant procedure financed by the Community budget, I have not been declared to be in serious breach of contract for failure to comply with my contractual obligations,

2.	In addition, the undersigned declares on his or her honour:

a)	that on the date of submission of the tender, the company or organisation I do represent and the staff proposed for this tender are not subject to a conflict of interests in the context of this invitation to tender; I undertake to inform GSA without delay of any change to this situation after the date of submission of the tender.

b)	that the information provided to GSA within the context of this invitation to tender is accurate, sincere and complete.

Done at ……………………………. on………………………………….

Name ………………………………...

Title ……………………………….

Signature:

# Footnotes

Article 93 of Council Regulation (EC, Euratom) No 1605/2002 of 25 June 2002 on the Financial Regulation applicable to the general budget of the European 	Communities (OJ L 248 of 16.9.2002)

For natural persons

This person must be included in the list of legal representatives; otherwise the signature on the tender will be invalidated.